## LINEAS BASE CREADAS
Nombre de la línea base | Fecha de creación | Elementos de configuración de que se compone

## Lineas Base
Elementos de configuración de las líneas base
LINEA-BASE | Phase0 | Phase1 | Phase2 |  |  |  | Phase3
Phase0 | Informal elicitation | FeasibilityAnalysis | Analisis | Diseño | Codificación | Pruebas
Phase1 | UseCasesFirstDraft+HighLevelDescription | Feasibility review | Use cases in extended format-IT1 | Class diagram/Data model-IT1
Phase2 | TechnicalAndEconomicalOffer | Use case model | Use cases in extended format review-IT1 | Class diagram review/Data model review-IT1
Analisis | MethodologySelection | Use case model review | Conceptual model/Data model draft-IT1 | Sequence diagrams/Wireframe model-IT1
Diseño | SCM Plan | Prioritization of use cases | Conceptual model review/Data model draft review-IT1 | Sequence diagrams review/Wireframe model review-IT1
Codificación | Quality Plan | Prioritization of use cases review | Operation Contracts-IT1 | Transition states diagram (optional)-IT1
Pruebas | SCM Plan Review | Definition of high-level use cases | Operation Contracts review-IT1 | Transition states diagrams review (optional)-IT1
Phase 3 | Estimation | Definition of high-level use cases review
Estimation review
Planning
Planning review